## Schedule and Gantt
Project Schedule and Gantt Chart
PROJECT TITLE |  | Welcome to the UT Dallas Fall 2021 Semester |  |  |  |  | PROJECT NAME | [6 empty] | Back To School
PROJECT MANAGER |  | Sahithi Sri Upputuri |  |  |  |  | DATE | [6 empty] | 2021-05-03
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE (Initiation) | [14 empty] | PHASE TWO (Project Planning) | [16 empty] | PHASE THREE(INITITAL PREPARATION) | [7 empty] | PHASE FOUR (PROJECT EXECUTION) | [29 empty] | PHASE FIVE (Deliverables and Review Management)
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 | [5 empty] | WEEK 7 |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Initiation |  | 2021-05-03 | 2021-05-21 | 15
1.1 | Kick off meeting | Project Manager | 2021-05-03 | 2021-05-03 | 1 | 100% | bar: WEEK 1 M
1.2 | Define scope and prime objectives | Project Manager | 2021-05-04 | 2021-05-06 | 3 | 100% | bar: WEEK 1 T to WEEK 1 R
1.3 | Identifying key personnel | Project Manager | 2021-05-07 | 2021-05-11 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.4 | Create project charter | Project Manager | 2021-05-12 | 2021-05-14 | 3 | 100% | bar: WEEK 2 W to WEEK 2 F
1.5 | Identify teams and set roles | Project Manager & Team Leads | 2021-05-17 | 2021-05-18 | 2 | 100% | bar: WEEK 3 M to WEEK 3 T
1.6 | Admin work for team communication | Admin | 2021-05-19 | 2021-05-20 | 2 | 100% | bar: WEEK 3 W to WEEK 3 R
1.7 | Identifying the risks at broader level | Project Manager & Team Leads | 2021-05-19 | 2021-05-21 | 3 | 100% | bar: WEEK 3 W to WEEK 3 F
2 | Project Planning |  | 2021-05-24 | 2021-06-15 | 17
2.1 | Create and Analyze business case | Project Manager | 2021-05-24 | 2021-05-26 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
2.2 | Prioritize goals and propose implementation phases | Project Manager | 2021-05-27 | 2021-05-28 | 2 | 100% | bar: WEEK 4 R to WEEK 4 F
2.3 | Create the Gantt chart and prepare schedules | Project Manager | 2021-05-31 | 2021-06-01 | 2 | 100% | bar: WEEK 5 M to WEEK 5 T
2.4 | Identify resources and define deliverables | Project Manager | 2021-06-02 | 2021-06-03 | 2 | 100% | bar: WEEK 5 W to WEEK 5 R
2.5 | Analyze Risks and Constraints | Project Manager & Team Leads | 2021-06-04 | 2021-06-07 | 2 | 100% | bar: WEEK 5 F to WEEK 6 M
2.6 | Budget Estimation | Treasurer | 2021-06-04 | 2021-06-07 | 2 | 100% | bar: WEEK 5 F to WEEK 6 M
2.7 | IT Support Planning | IT Lead | 2021-06-08 | 2021-06-11 | 4 | 100% | bar: WEEK 6 T to WEEK 6 F
2.8 | Planning for the Healthcare facilities | HealthCare Lead | 2021-06-08 | 2021-06-11 | 4 | 100% | bar: WEEK 6 T to WEEK 6 F
2.9 | International Students orientation planning | International house coordinator | 2021-06-08 | 2021-06-10 | 3 | 100% | bar: WEEK 6 T to WEEK 6 R
2.1 | Insurance planning | Insurance and accounting coordinator | 2021-06-08 | 2021-06-15 | 6 | 100% | bar: WEEK 6 T to WEEK 6 M
2.11 | Planning for the Housing facilities | Housing coordinator | 2021-06-08 | 2021-06-11 | 4 | 100% | bar: WEEK 6 T to WEEK 6 F
3 | Initial Preparation |  | 2021-06-08 | 2021-06-18 | 9
3.1 | Team orientation | Project Manager & Team Leads | 2021-06-08 | 2021-06-16 | 7 | 100% | bar: WEEK 7 T to WEEK 8 W
3.2 | Identify the technology solutions like zoom app | IT Lead | 2021-06-14 | 2021-06-16 | 3 | 100% | bar: WEEK 8 M to WEEK 8 W
3.3 | Proposing the mobile app for health checkups | IT Lead | 2021-06-17 | 2021-06-18 | 2 | 100% | bar: WEEK 8 R to WEEK 8 F
3.4 | Meeting with the student insurance providers | Insurance coordinator | 2021-06-16 | 2021-06-18 | 3 | 100% | bar: WEEK 8 W to WEEK 8 F
3.5 | Assessing housing requirements and hostel facilities | Housing coordinator | 2021-06-14 | 2021-06-18 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F
3.6 | Preparing guidelines for international student visa | International house coordinator | 2021-06-14 | 2021-06-18 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F
3.7 | Setting up the covid testing requirements | HealthCare Lead | 2021-06-14 | 2021-06-18 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F
100%
4 | Project Execution |  | 2021-06-21 | 2021-07-30 | 30
4.1 | Covid-19 safety precautions: | HealthCare Lead | 2021-06-21 | 2021-07-09 | 15 | 100% | bar: WEEK 9 M to WEEK 11 F
4.1.1 | Prepare Covid-19 Safety guidelines | HealthCare Lead | 2021-06-21 | 2021-06-22 | 2 | 100% | bar: WEEK 9 M to WEEK 9 T
4.1.2 | Development of mobile app for health checkups | HealthCare Lead | 2021-06-23 | 2021-06-24 | 2 | 100% | bar: WEEK 9 W to WEEK 9 R
4.1.3 | Setting up rapid testing sites & schedules | HealthCare Lead | 2021-06-25 | 2021-06-28 | 2 | 100% | bar: WEEK 9 F to WEEK 10 M
4.1.4 | Allocating the covid-19 onsite testing team | HealthCare Lead | 2021-06-29 | 2021-06-30 | 1 | 100% | bar: WEEK 10 T
4.1.5 | Placing a purchase order for Covid-19 vaccines | HealthCare Lead | 2021-06-30 | 2021-06-30 | 1 | 100% | bar: WEEK 10 W
4.1.6 | Procuring cleaning and sanitization equipment | Procurement Lead | 2021-07-01 | 2021-07-09 | 7 | 100% | bar: WEEK 10 R to WEEK 11 F
4.1.7 | Masks mandatory awareness boards | HealthCare Lead | 2021-07-01 | 2021-07-03 | 3 | 100% | bar: WEEK 10 R to WEEK 11 M
4.1.8 | Issuing Covid vaccination Id cards | HealthCare Lead | 2021-07-04 | 2021-07-06 | 3 | 100% | bar: WEEK 11 T to WEEK 11 R
4.1.9 | Training workshops for cleaning staff | HealthCare Lead | 2021-07-07 | 2021-07-09 | 3 | 100% | bar: WEEK 11 W to WEEK 11 F
4.2 | Finalizing the courses offered in the semester | Project Manager & Program coordinator | 2021-06-21 | 2021-06-30 | 8 | 100% | bar: WEEK 9 M to WEEK 10 F
4.3 | Scheduling classes and class room selection | Program coordinator | 2021-07-01 | 2021-07-02 | 2 | 100% | bar: WEEK 9 F to WEEK 10 M
4.4 | Allocating the professors to classes | Program coordinator | 2021-07-05 | 2021-07-06 | 2 | 100% | bar: WEEK 10 T to WEEK 10 W
4.5 | Allocating the student advisors | Program coordinator | 2021-07-07 | 2021-07-09 | 3 | 100% | bar: WEEK 10 R to WEEK 11 M
4.6 | Updating website and mobile app | IT Lead | 2021-06-21 | 2021-07-16 | 20 | 100% | bar: WEEK 9 M to WEEK 11 F
4.7 | Students email setup, access to online resources | Admin | 2021-06-21 | 2021-06-24 | 4 | 100% | bar: WEEK 9 M to WEEK 9 R
4.8 | vaccination requirements: | HealthCare Lead | 2021-07-12 | 2021-07-20 | 7 | 100% | bar: WEEK 11 W to WEEK 12 W
4.8.1 | sending vaccination remainder requests | HealthCare Lead | 2021-07-12 | 2021-07-13 | 2 | 100% | bar: WEEK 11 W to WEEK 11 R
4.8.2 | checking vaccination proof, docs verification | Admin | 2021-07-14 | 2021-07-20 | 5 | 100% | bar: WEEK 11 F to WEEK 12 R
4.9 | Procuring equipment | Procurement lead | 2021-06-21 | 2021-07-14 | 17 | 100% | bar: WEEK 9 M to WEEK 12 M
4.9.1 | For gym, library, and building facilities | Procurement lead | 2021-06-21 | 2021-06-30 | 7 | 100% | bar: WEEK 9 M to WEEK 10 T
4.9.2 | Quality testing of equipment | Admin | 2021-07-12 | 2021-07-14 | 3 | 100% | bar: WEEK 10 W
4.1 | Preparing for the student orientation | Program coordinator | 2021-07-12 | 2021-07-16 | 5 | 100% | bar: WEEK 10 R to WEEK 11 T
4.10.1 | Procurement of tshirts, goodies for orientation | Procurement lead | 2021-07-12 | 2021-07-16 | 4 | 100% | bar: WEEK 11 M to WEEK 11 W
4.10.2 | Scheduling the orientation sessions | Program coordinator | 2021-07-12 | 2021-07-14 | 3 | 100% | bar: WEEK 11 R to WEEK 11 F
4.11 | Preparing for the International students | International house coordinator | 2021-06-21 | 2021-06-21 | 1 | 100% | bar: WEEK 9 M
4.11.1 | Sending I20 and admin documents | International house coordinator | 2021-06-21 | 2021-06-25 | 5 | 100% | bar: WEEK 11 T to WEEK 11 F; WEEK 14 M to WEEK 14 R
4.11.2 | Arranging the travel | International house coordinator | 2021-06-28 | 2021-07-02 | 5 | 100% | bar: WEEK 12 M
4.11.3 | International student orientation preparation | International house coordinator | 2021-07-04 | 2021-07-06 | 3 | 100% | bar: WEEK 12 M to WEEK 12 T
4.12 | library membership provisioning for new students | Library Incharge | 2021-06-21 | 2021-06-25 | 5 | 100% | bar: WEEK 12 M to WEEK 13 T; WEEK 14 M to WEEK 14 T
4.13 | Disabled students’ accommodation arrangements | Admin | 2021-07-15 | 2021-07-16 | 2 | 100% | bar: WEEK 12 M to WEEK 12 F
4.14 | Allocating the housing details | Housing coordinator | 2021-06-21 | 2021-06-25 | 5 | 100% | bar: WEEK 13 F to WEEK 14 M
4.15 | Issuing Student ID cards | Admin | 2021-07-19 | 2021-07-21 | 3 | 100% | bar: WEEK 14 T to WEEK 14 W
4.16 | Creating the student accounts, enrolling in the student service center | Admin | 2021-07-22 | 2021-07-23 | 2 | 100% | bar: WEEK 14 R to WEEK 14 F
4.17 | Preparing for the department orientation | Program coordinator & Project Manager | 2021-07-15 | 2021-07-16 | 2 | 100% | bar: WEEK 13 R to WEEK 13 F
4.18 | Clearing finances and bill payment | Treasurer | 2021-06-21 | 2021-07-16 | 21 | 100% | bar: WEEK 9 M to WEEK 12 F
4.19 | Allocating Scholarships | Program Coordinator | 2021-07-19 | 2021-07-21 | 3 | 100% | bar: WEEK 13 M to WEEK 13 W
4.2 | Enrolling in the Health insurance plans for students | HealthCare Lead | 2021-07-14 | 2021-07-16 | 3 | 100% | bar: WEEK 12 W to WEEK 12 F
4.21 | Sharing campus life newsletter, facilities details | Admin | 2021-07-26 | 2021-07-26 | 1 | 100% | bar: WEEK 14 M
4.22 | Parking permits allocation | Admin | 2021-07-27 | 2021-07-28 | 2 | 100% | bar: WEEK 14 T to WEEK 14 W
4.23 | Logistics, travel arrangements like bus services | Admin | 2021-07-29 | 2021-07-30 | 2 | 100% | bar: WEEK 14 R to WEEK 14 F
4.24 | Preparing for the back to school welcome party | Project Manager & Team Leads | 2021-07-21 | 2021-07-23 | 2 | 100% | bar: WEEK 13 R to WEEK 13 F
5 | Deliverables and Review Management |  | 2021-08-02 | 2021-08-17 | 12
5.1 | Reviewing the Covid Scenario | Project Manager | 2021-08-02 | 2021-08-03 | 2 | 100% | bar: WEEK 15 M to WEEK 15 T
5.2 | Reviewing the Housing arrangements and facilities | Project Manager | 2021-08-04 | 2021-08-06 | 3 | 100% | bar: WEEK 15 W to WEEK 15 F
5.3 | Deployment and release of mobile health checkup app | IT Lead | 2021-08-02 | 2021-08-03 | 2 | 100% | bar: WEEK 15 M to WEEK 15 T
5.4 | IT support quality testing of course enrollment website | IT Lead | 2021-08-04 | 2021-08-06 | 3 | 100% | bar: WEEK 15 W to WEEK 15 F
5.5 | Final inspection of campus facilities for covid | HealthCare Lead | 2021-08-02 | 2021-08-04 | 3 | 100% | bar: WEEK 15 M to WEEK 15 W
5.5.1 | cleaning and sanitation arrangements | HealthCare Lead | 2021-08-05 | 2021-08-06 | 2 | 100% | bar: WEEK 15 R to WEEK 15 F
5.6 | Approving the insurance vendors, revisit if required | Project Manager | 2021-08-09 | 2021-08-10 | 2 | 100% | bar: WEEK 16 M to WEEK 16 T
5.7 | Budget calculations and financial review | Treasurer | 2021-08-02 | 2021-08-13 | 10 | 100% | bar: WEEK 15 M to WEEK 16 F
5.8 | Internal Review and Feedback collection | Project Manager | 2021-08-11 | 2021-08-12 | 2 | 100% | bar: WEEK 16 T to WEEK 16 W
5.9 | Project monitoring and support | Project Manager | 2021-08-13 | 2021-08-17 | 3 | 100% | bar: WEEK 16 R to WEEK 17 M
5.1
6 | Closure |  | 2021-08-18 | 2021-08-20 | 3
6.1 | Project closure andcommunication to management team | Project Manager | 2021-08-18 | 2021-08-18 | 1 | 100% | bar: WEEK 17 T
6.2 | Feedback Submission | Project Manager | 2021-08-19 | 2021-08-20 | 2 | 100% | bar: WEEK 17 W to WEEK 17 R
YOU CAN ADD MORE OR TAKE OUT LINES WITHIN YOUR SCHEDULE TO FIT YOUR PROJECT. THIS IS ONLY A TEMPLATE. | bar: WEEK 1 M to WEEK 15 T