## Risks
No. | Status | Risk | Impact | Prob'y | Impact Description | Submitted By | Date Identified | Status, Mitigation Strategy | Owner | Key Signs | Risk Index
ID | Open Closed | What is the risk event (or non-event)? | Low Medium High | Low Medium High | What is the effect if the risk occurs? | Person | Date | What is being done now and how is it progressing? What are the timescales for current actions? What would be done if the risk occurred? PREVENT / REDUCE / TRANSFER / CONTINGENCY / ACCEPT | Person | What are the early indicators? | Calculation based on Probability and Impact
R_001 | Open | Issue with new Covid-19 varients | High | Low | When the new varients are increasing within the USA, what are the preventive steps to be considered? Is going back to online classes if the new varient of covid-19 occures Is only an option? | Project manager | 2021-10-25 | At present the vaccines are working well for various varients. At present most of the people in the campus are fully-vaccinated. Need to implement the previous online classes or maintain the social distance and dividing into multiple sections for the in-person classes so that the students can come to the campus. Reduce the impact by applying the social distance and directions in the campus. | University health co-ordinator (Mr. A) | Dashboard with daily statistics within the campus shows the early predictions of new varients. | Low (risk = 3)
R_002 | Open | Availability of testing devices (temperature monitor, rapid detectors, nasel based tests) | Med | Med | For the large population based campus, availability of the resources are limited. Effictive utilization of these devices is really important if the risk happenes. | Project manager/team-lead | 2021-10-22 | AT present, there are multiple temperature sensors at the designated areas for daily checkup. Estimate a budget for the new devices purchare order with in the next 2-months. Effective utilization of the resources like temperature monitors with the valid calibration test daily. Preventing this risk by taking more purchase orders. | Class-room incharge/station incharge for a designated areas. (Ms. B) | Sanity test the present equipment dialy for the accurate estimation. Pre-order more equipment components for the future usage. | Medium (risk = 4 )
R_003 | Open | Mainiting social distance in the crowded areas like gym, restaurents, and public areas | Low | Low | At present most of the campus students got vaccination and it is easy to maintain the guidelines due to the prior experience. Apply the strict guidelines of social distancing if the risk occures. | Project member did the evaluation of the safety guidelines. | 2021-10-22 | At present, there are designated signs/indicators at the crowded places. Once the risk of Covid-19 increases, adding more strict guidelines will take a week in the crowded places. more strict rules will be imposed at these public places. This is preventive risk by following the guidlines. | Store incharges/ area incharges (Ms. C) | Adding more evaluators to know whether the students are following the posted guidelines. | Low (risk = 1)
R_004 | Open | Supply of the new booster dosage for the entire population in the next coming months | High | High | At presen the booster dosages are in preparation and need to make a plan for the distrubution to the entire campus with in next 1-3 months. | Project manager | 2021-10-25 | At present, follow the previous plan of vaccination which is based on the age and medical conditions as the priority for the booster dosage. However, it has to be more rapid compared to the last time. It is expecting for the coming 1-3 months to provide booster dosage for the whole campus. Allocate more slots for the rapid vaccination and allowing more time slots for the convience to the students and staff. Yes, this is the preventive risk by following the proper vaccination plan and its execution without any fail. | Health-care department within the campus and vaccination center (Mr. D) | Contact the local health-care department of Texas to know the availability of the booster dosage and its requirements like age-group and medical conditions. | High (risk = 9)
R_005 | Open | In accurate analysis of the daily health assessments for all students and staff for next couple of months. | High | Low | Reevaluate the daily data if any inconsistency occures in the data analysis. Post the data-analysis in the dash-board. This costs money, resources and time. | Project manager/lead engineer | 2021-10-22 | At present, collecting the dai;ly health assemsent and following the data analysis shows the chart of healthy/might get infected/infected persons statistics using machine learning techniques. At present it is taking around 6 hours to generate these charts/histograms. if the risk occures of inaccurate estimation of results from a sample population, then it is better to verify monitoring devices and checking the algorithms again on the present data. Using the latest machine learning models on the large models (such as AWS platforms) for the accurate estimation of the data with in the less time could be a preventive actions. | Software center analysis/campus data co-ordinator (MR. E) | Verify the accuracy of the testing devices and algorithms regularly for checking any inconsistency can be the early indicator. Verify the same using automated platforms will be helpful for faster results. | Medium (risk = 3 )
R_006 | Open | Limited class room discussion during the office hours by following the guidelines | Low | Low | Provide proper guidelines to maintain the discussion room for the recitation classes/office hours with either TA's or Professors or other student members. | Teaching Assistant/Professor of the class | 2021-10-01 | Already, we solved this risk by incorporating the recitation/office hours into a limited capacity students and following the strict guidelines. Since this is already executed, relaxation in this method can be provided if the number of detecttive cases are small. Again, if the situation is bad with covid-19, then apply the conditions of social distance strictly. This is the reduce type of risk and can be completly preventive if the guidlines are followed. | Teaching Assistant/Professor of the class (Ms. F) | Checking the dashboard regualrly and imposing the safety guidelines can be the early indication here. | Low (risk = 1 and it is already resolved )

## Issues
No. | Status | Priority | Issue | Date Identified | Submitted By | Category | Action/Comments | Owner | Assigned To | Target Date
ID | Open Closed | Low Medium High | What is the issue? | Date | Person | Categorization of issue (e.g.., Scope, Budget, Testing) | What is being done now and how is it progressing? What are the timescales for current actions? | Resolution Owner | Person | Target Date
1 | Closed | Low | Posted safety guidelines | 2021-08-22 | Safety incharge | Budget | posted the respective places the proper guidelines | place safety incharge | Mr. A | 2021-10-22
2 | Closed | Low | Daily tests | 2021-08-22 | Safety incharge | testing | Need test eqipment for the daily tests on a small random population | University health incharges | Ms. B | 2021-10-22
3 | Open | Med | update the covid-19 dashboard | 2021-10-25 | Software lead | Testing | Adding additional graphs for the daily dashboard display for more intutive analysis of the present covid-19 in the campus | Developer | Mr. C | 2021-12-15
4 | Open | High | New weblink for the next booster dosage slots | 2021-10-24 | project manager | Budget, testing of link/web page | At present, new web page with more options are provided for the booster dosage, however, this web-page needs lot of testing before rolling to the students/staff. | Software developer | Ms. D | 2021-11-15
5 | Open | High | Quote for the new vaccines from Pfizer, Moderna and J&J | 2021-10-23 | project manager/lead | Budget, project plan for different vaccines purchase order | Maintain a complete project plan by taking the statistics of the current students/staff and their previous vaccination records. Here the next dosage order depends on the previous vaccinations. Hence new oder of vaccination requires complete analysis of the previous data. | Lead and Software developer to present the data before taking new purchase order | Ms. E, Ms. F and Mr. D | 2021-11-01
6 | Closed | High | Implementation of flu vaccination shots for the winter season. | 2021-10-15 | manager | Budget | For the coming winter season, all population received the complete flu shots to reduce the risk in this time. | university health-care department | Ms. F and Mr. G | 2021-10-01

## Weights (hidden)
Weight
High | 6
Med | 3
Low | 1
Evaluation
> High | 4
< Low | 1.7
Y
N
| High | 3
| Med | 2
| Low | 1
Open
Closed
Closed -> Issue
1 - High
2 - Med
3 - Low
Open
Closed